TERMS OF REFERENCE TO HIRE AN INDIVIDUAL CONSULTANT TO REVIEW THE QUALITY OF EDUTAINMENT EPISODES AND ASSESS THEIR EFFECT ON IMPROVING LEARNING ENVIRONMENT IN THE CLASSROOM

TERMS OF REFERENCE TO HIRE AN INDIVIDUAL CONSULTANT TO REVIEW THE QUALITY OF EDUTAINMENT EPISODES AND ASSESS THEIR EFFECT ON IMPROVING LEARNING ENVIRONMENT IN THE CLASSROOM

- BACKGROUND AND CONTEXT

- BACKGROUND AND CONTEXT

The Government of Rwanda (GoR) through the Ministry of Education (MINEDUC) and its implementing agency Rwanda Basic Education Board (REB) are implementing a project of Rwanda Quality Basic Education for Human Capital Development Project (QBEP) funded by the World Bank with life span of five years since 2019-2024 in the parent project and the second additional financing to the project until 2027. The objective of this project is to strengthen Rwanda’s Basic Education System through investments in teacher preparation, recruitment, and professional development (to improve teaching practice) as well as in infrastructure and teaching and learning resources (to enhance students’ attendance and learning environment). Through this project, the Government of Rwanda seeks to equip more Rwandan children with the foundational skills and competencies required for success in the country’s modernizing economy.

The project is further set to contribute to efforts of reducing poverty and promoting shared prosperity thus enabling Rwanda to realize its goal for Vision 2050 of becoming a high-income country (Project Appraisal Document, 2019). Among subcomponents Rwanda Quality Basic Education for Human Capital Development Project focuses on includes enriching early learning environment for preprimary and lower primary school-age children through the development of engaging and inclusive educational entertainment content (such as animated cartoons) to supplement learning in homes and schools. This activity is implemented and coordinated through REB in-house production initiative with the engagement of local experts such as animators, screen writers, illustrators, sign language interpreters, audio narrators/vocalists and multimedia (video and Audio) producers. It is targeted to produce 178 episodes for 4 years in four phases. So far, REB has been able to produce 96 edutainment animated episodes in the last two phases. Despite this milestone, little is known by REB if is improvement in learning environment in the classrooms.  This necessitated a need to conduct a pilot study among 60 learners including LWDs and 120 teachers from nursery and lower primary grades from 10 schools including schools for special needs representing 10 districts (Karongi, Rusizi, Gakenke, Musanze, Muhanga, Huye, Kayonza, Gatsibo, Gasabo and Nyarugenge) in Rwanda. The pilot study will be limited to the first 48 episodes that are now available to learners, teachers and schools through existing media channels. The study will use a qualitative and observation methodology whereby the focus group discussion with key users (learners and teachers) and classroom observations (for a span of 1 week) will be organized at the school level.  The pilot study will focus on the quality of episodes, learners’ and teachers’ level of access to episodes, participation of learners including LWD (learners with disability) in a lesson, interest of learners to watch episodes during learning, effective utilization of episodes by teachers and learners during lesson delivery and learning, and contribution on individual learning. The study will be conducted by June 2023. Prior this, Preliminary activities including additional delivery of episodes to schools through possible physical ways, training teachers to effectively utilize these episodes in classroom during lesson delivery and granting teachers 1 month of practicing acquired teaching skills in classroom will be done. However to ensure smooth implementation of this activity, REB in collaboration with the World bank intends to hire an experienced individual consultant to provide technical support in reviewing the quality of the first 48 edutainment episodes in schools and their effect on improving learning for  learners including LWDs.

- OBJECTIVES OF THE ASSIGNMENT

- General Objective

The overarching objective of the assignment is to review the quality of 48 edutainment episodes used in schools and their effect on improving learning for all learners including LWDs and provide evidence-based recommendations for future improvement of episodes.

- Specific Objectives

- To assess if teachers and learners are able to access edutainment episodes in classroom and home;

- To engage teachers and learners to understand how 48 episodes used in schools are improving learning to all learners including LWDs;

- To review the quality of entertainment, multimedia, education and inclusive aspects of 48 edutainment animated episodes for preprimary and lower primary grades;

- To develop a quality assurance rubric/checklist tailored to integrated multimedia objects for REB in-house team to use in future edutainment episodes production initiatives

- To provide actionable recommendations to REB aiming to improve the quality, inclusivity, relevance and effective utilization of edutainment episodes

- METHODOLOGY AND APPROACH

The consultant will define the methodology relevant to the assignment. The consultant will be required to organize the inception meetings with REB technical team to have a glimpse of edutainment episodes’ project and the anticipated changes in the classroom. As a basis, the consultant is strongly encouraged to piggy-back on existing project documents related with the assignment and episodes already available to the public for analysis and triangulation purposes. Considering the usability aspect (learnability, effectiveness, access to use and satisfaction) of edutainment episodes, the consultant will engage key informants (teachers and learners) to assess how 48 edutainment episodes used in school have increased learners’ motivation and lesson participation for all learners including learners with disability. Considering insights from benchmarks from the region/international level on similar projects and feedback from users, the consultant will review the quality of multimedia (text, images, audio including volume appropriateness and sound effects, and videos), entertainment (storytelling, games, animation and visualization), education (moral values and various learning theories) and inclusive (SL video window size and placement on the screen, lip speaking pace and alignment, SL grammar or vocabulary with its compliance with Rwanda SL standards, SL context, and video captions) aspects.

The consultant will leverage use the updated Sign Language production rubric/guidelines developed by the world bank team to review the quality of SLVs embedded in the episodes. Based on these key themes, the consultant will ensure that structured interviews for key informants (teachers and learners) and well aligned classroom observation tools to use in classrooms in selected schools including Schools for special needs are well designed, piloted, validated and digitized using real-time data collection system (preferably open-source software) and thereafter will train data collectors on how to administer these tools.

The consultant will organize data in accordance to key themes and other themes emerged from data and where possible align them to the production stages (screen writing, storyboarding, multimedia production, sign language production and animation development) and usability aspects of the episodes.

- DELIVERABLES

The following are the key deliverable for the assignment

| No | Deliverables | Required document | Period |
| --- | --- | --- | --- |
| 1 | Submission of a draft inception report to the client (REB) and be reviewed and validated by a designated technical team from CTLR and SPIU | Draft inception report | 5 days |
| 2 | Addressing comments and inputs from the REB Technical team and stakeholders. | Approved Inception Report submitted | 5 days |
| 3 | Design and digitize interview guides and classroom observation tools tailored to key informants (teachers and learners) and target grades (N1-N2 and P1-P3); | Draft data collection validated before its usage | 10 days |
| 4 | Piloting of abovementioned tools with teams from REB, and key stakeholders at the school level (in classroom). | Flash-report on tools validated and piloted | 5 days |
| 5 | Data collection exercise, data analysis and compilation of the draft report with actionable recommendations for further improvement of the episodes putting in consideration the quality, inclusivity, relevance and effective utilization of edutainment episodes. | Clean datasets and codes with emerging themes used to analyze data; | 10 days |
|  | Develop a quality assurance rubric/checklist tailored to multimedia objects of episodes for REB in-house team to consider in future episode production initiatives | QA rubric for episodes | 5 days |
| 6 | Present the draft report to REB designated technical team for review and validation | Report | 5 days |
| 7 | Address comments after review and submit final report to the client (REB) | Final report | 5 days |
|  | Total |  | 50 days |

- DESIRED EDUCATION QUALIFICATION

- Advanced degree PhD or Master’s Degree in Instructional design/ Educational technology with experience of 4 years in similar work proven by a certificate of good completion;

- Advanced degree PhD or Master’s Degree in Project Management, Development studies, Economics; Social Sciences and Measurement and Assessment profile with experience of 5 years in the assignment of the same nature.

- DESIRED TECHNICAL REQUIREMENT

- Technical skills in educational technology /information technology including graphic design, digital content development, including animated audio-visual material

- Vast knowledge in multimedia learning, universal design for learning, learner’s experience design and 2D/3D animation technology;

- Strong analytical and report writing skills;

- Experience in working with development partners including local and or intentional organizations will be an added value.

- Consultant should have excellent communication skills, both written and oral in English, working knowledge of French and or Kinyarwanda will be an added advantage

- Strong and proven evaluation/assessment research and analytical skills

- Initiative and ability to organise her/his work independently without supervision

- Proven ability to deliver output working under tight deadlines.

- Be flexible and responsive to changes as part of the review and feedback process.

- Knowledge in educational and assessing behavioral change among teachers, learners and parents;

- Prior experience in conducting Impact Assessment surveys and tracking social behavior change among teachers/learners /parents.

- EVALUATION CRITERIA OF TECHNICAL PROPOSALS ARE:

| No | Criteria | Marks |
| --- | --- | --- |
| 1 | Understanding ToRs, detailed methodology and work plan for providing technical and coordination support in assessing the impact of edutainment animated episodes in classroom: - Understanding of ToRs and mastery of the assignment (10 Points) - Detailed Methodology (35 Points) - Work Plan (5 Points) | 50 |
| 2 | Academic qualifications and key skills to meet the terms of reference (Justified by provided supporting documents (copy of degree Only Notified degree certificates will be accepted (15 Points) | 20 |
| 3 | Possess at least two (2) certificates of good completion to the similar work performed (10 points) | 10 |
| 4 | An updated CV stating details of educational qualifications and relevant experience: - Updated and detailed CV (10 points) - At least 5 years relevant experience in conducting impact assessment or surveys or studies (detailed in CV) related with the assignment in hand (10 Points); | 20 |
|  | Total | 100 |

Note: Weight given to the Technical proposal during the evaluation of this tender is 85%, while financial proposal is weighted at 15%. However, the Minimum Technical Score to pass on the next step of financial evaluation is 80%.

- REPORTING REQIREMENTS

For all contractual issues, the individual consultant will report to REB-SPIU Coordination office under Quality Basic Education (QBE) Program. For technical issues the contractor will liaise with CTLR department. All deliverables must be approved by a designated technical team from CTLR Department and REB-SPIU to be considered complete.

- PAYMENT MODALITY

The consultant will be paid after completion of the deliverables as follows:

- 30% upon the submission and acceptance of the inception report;

- 40% upon the submission and acceptance of the first draft report of the work;

- 30% upon the submission and acceptance of a final reports.

On the final submission report, a consultant will submit three (3) hard copies to REB-SPIU and CTLR Department.

- APPLICATION PROCEDURE

Interested applicants must submit the following dossiers via e-procurement/Umucyo platform (https://www.umucyo.gov.rw/).

The application will be addressed to Director General of Rwanda Basic Education Board including the technical and financial proposals, a methodology for the assignment, including a detailed work plan in line with the Terms of Reference, updated personnel CV and certificates of good completion of previous similar works, a copy of ID Copy/Passport and copies of notified degree certificates on or before the date and time specified in the e-procurement system.